## WBD
Date | Phase | Subject | Begin time | End time | Hours | Phases | Subs | Subjects | Hours
2020-01-05 | 1 | 1.1 - 1.2 - 1.3 | 11:00 | 16:00 | 5 | Phase 1: Analyse | 1.1 | Plan of Approach
[7 empty] | 1.2 | Setting up project
[7 empty] | 1.3 | WBD
[6 empty] | Phase 2: Research | 2.1 | OpenGL
[7 empty] | 2.2 | Tutorials
[7 empty] | 2.3 | Examples
[6 empty] | Phase 3: Implementation | 3.1 | Checkers board
[7 empty] | 3.2 | Pawns
[7 empty] | 3.3 | Game
[7 empty] | 3.4 | Options
[7 empty] | 3.5 | Chess
[6 empty] | Phase 4: Finalization | 4.1 | Review documents
[7 empty] | 4.2 | Proof of concept
[7 empty] | 4.3 | Assessment

## Planning
Week | Subjects | Phase | Deadline | Phases | Subs | Subjects
1 |  |  |  | Phase 1: Analyse | 1.1 | Plan of Approach
2 | Introduction | Phase 1 |  |  | 1.2 | Setting up project
2a | Analyses / Setting up project | Phase 1 |  |  | 1.3 | WBD
3 | Analyses / Research | Phase 1 + 2 |  | Phase 2: Research | 2.1 | OpenGL
4 | Research | Phase 2 |  |  | 2.2 | Tutorials
5 | Implementation | Phase 3 |  |  | 2.3 | Examples
6 | Implementation | Phase 3 | Assessment | Phase 3: Implementation | 3.1 | Checkers board
7 | Implementation / Finalization | Phase 3 + 4 | Assessment |  | 3.2 | Pawns
8 | Implementation / Finalization | Phase 3 + 4 | Assessment |  | 3.3 | Game
9 | Implementation / Finalization | Phase 3 + 4 | Resit assessment |  | 3.4 | Options
10 | Implementation / Finalization | Phase 3 + 4 | Resit assessment |  | 3.5 | Chess
|  |  |  | Phase 4: Finalization | 4.1 | Review documents
[5 empty] | 4.2 | Proof of concept
[5 empty] | 4.3 | Assessment